,

Climate Change Strategy (2025-30)
Working together today to build a more sustainable tomorrow

# Executive Summary:

Set against a backdrop of rising living costs, slow economic growth, and increased demand on services, climate action may not seem like the most obvious way to support households in Redbridge. However, climate action serves as a powerful tool in supporting broader policy outcomes that benefit everyone living and working in our borough and helps to improve local health outcomes, stimulates the local economy, and bolsters financial resilience within the community.
Global greenhouse gas emissions have soared to unprecedented levels to a point that severe weather events and increasingly extreme temperatures have become more commonplace which has pushed vulnerable households into fuel poverty. We need to ensure that everyone living and working in Redbridge can thrive and live a healthy, comfortable life, which is why climate action is essential.
Whilst the climate conditions have been changing, so has our borough as Redbridge has become more densely populated with the local population increasing by 11.2% over the past decade to an impressive 310,130 residents[1]. Redbridge has also been growing at a far greater rate than the national average of 6.6%, and this has resulted in our borough being ranked in the top 10% of most densely populated local authority areas in England[2]. With our population only projected to increase even more over the coming decade, climate action will become more important than ever as our roads will become even busier which will affect local air quality, we will consume more goods, produce more waste, and local services may be strained. There will also be an increased demand for new high-quality housing and existing homes will need to be upgraded as a recent report highlighted that properties in Redbridge scored the lowest average energy efficiency ratings in London[3].
[1] How life has changed in the City of London: Census 2021 – Office of National Statistics - 2023
[2] How life has changed in Redbridge: Census 2021 – Office of National Statistics - 2023
[3] Domestic Energy Performance Certificates for all dwellings by energy efficiency rating – Department for Levelling Up, Housing and Communities - 2025
However, by taking steps such as retrofitting our homes with better insulation and incorporating renewable energy technologies, we can significantly reduce household bills, protect households from volatility within the energy market and make it easier for families to manage their finances. Investing in flooding infrastructure and adapting our homes will also protect properties from being damaged and ensure that residents can live comfortably in an ever-changing climate. Empowering residents with green skills and supporting sustainability within the local market will improve local economic outcomes as employment prospects will be improved, high streets will be stimulated, and residents will have access to more employment opportunities.
Supporting the transition to electric vehicles and encouraging active travel within the community will also reduce harmful transport emissions and drastically improve local air quality which will enable residents to lead more active, healthier lifestyles with a reduced chance of developing respiratory conditions. Enhancing our parks and community gardens will also ensure that residents have greater access to high quality green spaces which will support the mental wellbeing of the community – a factor that was especially important during the COVID-19 pandemic.
To achieve this, the Council has created a new Climate Change Strategy which sets out the Council’s ambition of Redbridge becoming net zero by 2050 which is in line with national carbon targets. The strategy includes 135 actions that services aim to deliver over the coming years which fall under the following 5 major themes:
1. Energy Efficient Modern Buildings
2. Sustainable Connected Neighbourhoods
3. A Climate Resilient Green Borough
4. A Thriving Green Economy
5. Climate Conscious Communities
These themes have been designed using data from the borough’s emissions profile to enable the Council to accurately target interventions that will influence emissions reductions across key sectors in Redbridge and boost the economic, social, health and environmental outcomes for our residents. Services across the entire organisation have committed to delivering actions that will support a broad range of priorities which includes improving sustainability within the local business sector, enhancing the energy efficiency of homes in the borough, supporting the transition to electric vehicles through the delivery of key infrastructure, greening urban spaces to boost local biodiversity and supporting residents to access opportunities within the green economy. This robust approach aligns with the major themes and priorities of the Redbridge Plan (2022-2026), particularly the 'Clean and Green' theme, and reinforces the Council’s commitment to a more sustainable future. However, this summary is just a snapshot of the actions that the Council plans to deliver so please read through the full Strategy to find out more information on all of the 135 actions.
In addition, analysis of central government data shows that Redbridge ranks in the middle range for deprivation levels when compared to all areas in England however areas such as Loxford, Clementswood and Valentines rank among the top 10-20% of most deprived areas in the country[4]. To ensure an equitable transition to net zero, the Council will prioritise actions to address fuel poverty and support underserved areas of the community through the deployment of targeted initiatives, grant programmes and retrofit projects for energy efficiency improvements. By focusing on the most vulnerable communities first the Councill aims to promote fairness and inclusivity in our Strategy which will help bridge the gap in energy equity and foster a more resilient and just community.
[4] Indices of Deprivation – Department for Levelling Up, Housing and Communities - 2019
The Council also recognises that our goals cannot be achieved by working alone and close collaboration with regional and central government bodies and key local organisations will be essential. The borough will need a significant increase in resources and capacity to effectively tackle the climate emergency which is why the Council will identify and apply for additional funding and engage effectively with national government and external partners to ensure that the needs of Redbridge are met. The Council will also review any emerging green financing mechanisms that may enable services to leverage greater funding for local climate initiatives and officers will also implement robust monitoring and reporting systems to ensure that there is clear transparency on the progress that the Council and borough is making in playing our part in reducing our emissions.
Finally, meeting the challenge of the climate emergency may seem like a huge task to scale but if we all work together and act now, we can secure a safer, more sustainable future for Redbridge and improve the lives of everyone living and working in the borough. We all have an important role to play, no matter how big or small, in ensuring that we reduce our emissions and support the borough’s transition to net zero. We will all need to work together to ensure that every resident is protected from the changing climate conditions and all actions from major infrastructure programmes such as the wide scale roll out of electric vehicle charge points to grass roots projects such as the delivery of eco skills workshops within the community will all be essential in ensuring that we change the trajectory of Redbridge’s future.

# Theme 1: Energy-Efficient Modern Buildings

Introduction: How we heat and power our buildings accounts for the largest sector of emissions here in Redbridge and these emissions cover a diverse array of building types including residential homes, public buildings, offices, and retail shops. These type of stationary energy emissions also translate into energy bills for households, local businesses, and community groups and so measures aimed at tackling these emissions can produce significant financial savings.
To start reducing emissions from our buildings the Council has developed the theme ‘Energy Efficient Modern Buildings’ which features a significant programme of work which aims to enhance the energy efficiency of Council-owned buildings and homes, promote the adoption of renewable energy technologies, leverage local planning policy to ensure that developers implement sustainable building practices and foster collaboration within the local business sector to improve sustainability.
Long-Term Vision: All buildings in Redbridge have high energy efficiency ratings and are powered by renewable energy which means running costs are low and the borough is protected from volatility within the energy market. New developments prioritise sustainability, ensuring that everyone in the borough is protected from the changing climate in a cost-effective manner. Decarbonisation is a shared goal and responsibility of all residents, businesses, and community groups in the borough.

Key achievements delivered so far:
- 100% of the electricity that we use for street lighting, Council-owned buildings, and communal areas of the Council’s housing stock switched to green electricity.
- Over £2.2m of funding secured to support low-income households with energy efficiency measures and 100+ properties in the borough retrofitted to EPC C.
- Building Management Systems (BMS) installed at over 35 Council-owned buildings to enable more accurate energy consumption monitoring and allow interventions to be targeted more efficiently.
- Over 86% of the Council’s housing stock assessed to help target energy efficiency improvements and to inform decarbonisation strategies.
- A Carbon Offset Fund was established and to date building developers have provided £508,677 to compensate for the emissions produced by local building projects.
- Since 2022, all new non-residential Council buildings are required to meet the highest energy efficiency standards -BREEAM ‘Excellent’.
- Various schools, such as Churchfields Junior School, supported with solar panel installation on their buildings and the plans are to expand the support to more schools in this Strategy.

Key Priorities:
1. Decarbonising The Corporate Estate
2. Driving Forward The Use Of Renewable Energy
3. Partnering With Local Businesses On Sustainability
4. Upgrading Homes In The Borough For 2030
5. Advancing Sustainable Building Practices

Decarbonising The Corporate Estate
At a time when the demand for services is soaring due to the high cost of living and the Council’s budget is under pressure, optimising the operational efficiency of our buildings to cut down the Council’s energy bills is of vital importance to ensure that more funding can go to supporting our residents. By conducting comprehensive studies and developing a detailed decarbonisation plan, the Council can systematically improve the operational efficiency and sustainability of our buildings which will lead to greater energy savings, reduce the Council’s reliance on fossil fuels, and lower building maintenance costs. By promoting successful carbon reduction projects, the Council can inspire greater community action on climate change and position the Council as a leader on climate action in local government. Additionally, by taking steps to improve the energy efficiency of our buildings, the Council can set a precedent for private sector organisations to follow which helps to encourage greater collective action on tackling the climate emergency.

Driving Forward The Use Of Renewable Energy
The widespread adoption of renewable energy systems helps to create a low carbon economy and enables households, local businesses and community groups to yield significant savings by generating their own green electricity. These initiatives build financial resilience within the community and make valuable contributes to national energy security as communities are less vulnerable to volatility within the energy market. By providing information on grant funding opportunities and conducting feasibility studies for solar panel installations, the Council can empower local communities to develop and use sustainable energy solutions more readily. Encouraging schools to adopt renewable energy measures also reduces the carbon footprints of educational buildings and builds long term engagement from students on the climate change agenda. Collaboration with other local authorities also enables services to enhance local strategies for more effective decarbonisation action and further promotes energy independence within the community.

Partnering With Local Businesses On Sustainability
By prioritising sustainability, businesses can become more competitive as greater operational efficiency means lower overhead costs. Partnering with local businesses also enables the Council to foster greater collaboration on climate action in Redbridge and drive innovation within the local business sector. By delivering quarterly workshops and providing sustainability toolkits to local businesses we can equip the local economy with the knowledge and desire to adopt more sustainable practices. The Council can also reduce the emissions generated by waste in the local business sector by promoting pan-London initiatives and engaging with local food businesses and the care sector. By providing close support to the local business sector, we can help businesses reduce their environmental impact and improve their operational efficiency which provides valuable contributions to regional and national climate goals.

Upgrading Homes In The Borough For 2030
With properties in Redbridge ranking the worst for energy efficiency in London, significant work needs to take place to retrofit our homes and ensure that residents can live comfortably through more frequent extreme weather conditions. Retrofit measures also play an integral role in safeguarding households from fuel poverty as sufficiently adapted homes generate lower energy bills in the winter and enable households to manage their finances more effectively. By delivering grant programmes and developing retrofit projects for the most vulnerable in Redbridge, the Council can ensure an equitable approach to property decarbonisation in the borough and reduce the emissions generated from heating and powering our homes. Major retrofit programmes and targeted energy efficiency improvements will also help to enhance climate resilience within the community and by providing advice to homeowners and landlords we can empower private homeowners to make energy-efficient improvements and improve sustainability within the local housing market.

Advancing Sustainable Building Practices
Driving forward the use of sustainable building practices helps to ensure the highest environmental standards and reduce the carbon emissions produced by local development. By taking steps, such as refreshing the Local Plan and ensuring that waste segregation systems are incorporated into new building designs, we can enhance sustainability within the local building market. The Council will also continue securing carbon offset contributions from new developments, strive for BREEAM Excellent certification for non-residential developments, implement ‘fabric first’ principles and drive forward policies from the London Plan to ensure that new developments incorporate renewable energy and achieve high energy efficiency standards. By incorporating innovative measures such as renewable energy generation and low-carbon heating systems we can promote sustainable development here in Redbridge which is a vital step in supporting the borough’s transition to net zero and makes valuable contributions to national climate goals.

Commitments		Outcomes
Detail	Timeframe	Carbon Reduction	Climate Resilience	Improved Public Health	Saving Money	Protect Biodiversity
Decarbonising the Corporate Estate
1C The Council will commission comprehensive studies and feasibility assessments to be conducted on all corporate buildings contingent on additional funding being secured.	Ongoing	X	X		X
2C The Council will develop a detailed 10-year Decarbonisation Plan for the Corporate Estate based on the desktop studies, outlining specific projects, timelines, and funding sources to ensure effective resource allocation and steady progress towards sustainability goals.	Medium-term (2-5 years)	X	X		X
3C The Council will install a cost-effective solar panel system on Lynton House to achieve significant energy bill savings within four years, setting a model for future renewable energy projects and reducing the building's carbon footprint.	Short-term / (0-2 years)	X	X		X
4C The Council will integrate decarbonisation measures, including renewable energy installations, heat pumps, and other energy efficiency improvements, into all future capital projects on schools and council-owned buildings to maximise the environmental benefits and long-term cost savings.	Ongoing	X	X	X	X
5C The Council will actively promote its carbon reduction and sustainability projects to inspire and mobilise community action on climate change.	Ongoing	X	X	X	X	X
6C The Council will as part of the Capital Maintenance Programme replace conventional lighting with LED lightings, aiming to complete 4 buildings per annum.	Ongoing	X			X
Driving Forward the Use Of Renewable Energy
7C The Council will conduct desktop studies to assess the feasibility of installing solar panels on corporate buildings and any applicable leisure facilities and these studies will evaluate factors such as solar resource availability, roof space, structural integrity, and energy demand.	Long-term / (5-10 years)	X			X
8A The Council will actively encourage schools in installing solar panel systems and other renewable energy measures by leveraging external funding sources and partnerships, aiming for 10 schools per year to undertake these initiatives with the target of equipping all school buildings within 10 years.	Ongoing	X			X
9C The Council will establish or build on connections with other local authorities to exchange knowledge and replicate best practices in decarbonising the corporate estate.	Ongoing	X	X		X
10A The Council will provide comprehensive information on potential grant funding opportunities for renewable energy projects for households, community groups and local faith organisations. Additionally, the Council will conduct ongoing horizon scanning to identify new and relevant funding sources, ensuring timely and valuable support for sustainability initiatives where feasible.	Ongoing	X	X		X
Partnering With Local Businesses On Sustainability
11A The Council will deliver quarterly business workshops which will include information such as actionable changes that businesses can implement to reduce carbon emissions from their operations and possibly toolkits that businesses could use which will further promote sustainability within the local business sector.	Short-term (0-2 years)	X	X	X	X
12A The Council will promote pan-London initiatives and relevant programmes that support businesses in achieving net zero, reduce waste from their operations, adopt more sustainable practices, and integrate long-term sustainability measures into their daily operations.	Short-term (0-2 years)	X	X	X	X
13A The Council will partner with Care Provider Voice to support local businesses within the care sector in developing and implementing appropriate environmental and sustainability management plans. This collaboration will ensure that these businesses meet the Care Quality Commission's requirements for sustainable practices.	Short-term (0-2 years)	X	X	X	X
14A The Council will explore the development of a programme to support businesses in Redbridge in becoming more sustainable and reducing their carbon footprint. This programme will explore opportunities on providing sustainability advice and conducting energy audits to identify areas for improvement.	Medium-term (2-5 years)	X	X	X	X
Upgrading Homes In The Borough For 2030
15A The Council will continue to implement the Go Green Grant programme and collaborate with the GLA to provide Warm Home grants, enhancing home energy efficiency and reducing heating costs for low-income households. Additionally, the Council will identify and secure funding for further schemes, ensuring sustained support and effective implementation through ongoing collaboration with the GLA and other central bodies.	Medium-term (2-5 years)	X	X	X	X
16C The Council will develop and implement a comprehensive Retrofit Route Map to enhance the energy efficiency of our social housing stock. This initiative will prioritise properties in fuel poverty, ensuring that those most in need receive support first.	Long-term / (5-10 years)	X	X	X	X
17C The Council will deliver a retrofit pilot project to install energy efficiency measures in 12 Council-owned properties located in Hainault. This project will specifically target low-income, vulnerable households to ensure they benefit from reduced energy costs and improved living conditions.	Ongoing	X	X	X	X
18C The Council will deliver a major retrofit programme for 323 Council-owned properties in Redbridge, contingent upon securing the necessary funding. This programme will use the insights and learnings gained from the Hainault pilot project and the programme will prioritise properties in fuel poverty.	Medium-term (2-5 years)	X	X	X	X
19A The Council will create a Redbridge Retrofit Route Map for all privately owned residential properties in the borough, leveraging insights from the existing Retrofit Route Map.	Medium-term (2-5 years)	X	X	X	X
20 The Council will submit funding applications to various public and private sector funding streams to secure additional resources for retrofit programmes here in Redbridge.	Ongoing	X	X	X	X
21C The Council will survey and analyse the organisation's housing stock to identify areas which require energy efficiency improvements and following this analysis, the Council will implement a targeted programme prioritising households in fuel poverty.	Ongoing	X	X	X	X
22A The Council will provide comprehensive advice for homeowners and private landlords aiming to enhance the energy efficiency of their properties. This guidance will highlight available grants and resources, particularly those designed for low-income and vulnerable households.	Ongoing	X	X	X	X
23A The Council will continue to enforce Minimum Energy Efficiency Standards (MEES) for all properties within the private rented sector to promote sustainability within the local housing market.	Ongoing	X	X	X	X
24A The Council will maintain ongoing engagement with landlords, tenants, and other stakeholders through relevant forums to continuously promote sustainability and innovation within the private rented sector.	Ongoing	X	X	X	X
Advancing Sustainable Building Practices
25A The Council will refresh the Council’s Local Plan when future budgets and capacity allow, ensuring it reflects current sustainable development priorities and community needs.	Medium-term (2-5 years)	X	X	X	X	X
26A The Council will ensure planning conditions enable the inclusion of waste segregation systems in building designs to future-proof them against evolving legislation.	Ongoing	X
27A The Council will continue to secure and collect carbon offset contributions from all appropriate developments to the Carbon Offset Fund and maintain regular reporting to the Greater London Authority (GLA).	Ongoing	X	X	X	X	X
28C The Council will continue to aim for new non-residential buildings to achieve BREEAM Excellent certification provided that full consideration is given to the affordability of sustainability measures.	Ongoing	X	X	X	X
29C The Council will consider installing individual measures for non-residential capital programmes and residential Housing Revenue Account (HRA) programmes, such as solar panel systems and heat source pumps. This approach will be taken in instances where meeting the full BREEAM criteria is not viable, ensuring that the Council still achieves significant energy efficiency improvements.	Ongoing	X	X	X	X
30A The Council will request developers provide evidence of their implementation of ‘fabric first’ principles in building design and this will involve prioritising fabric efficiency by reducing opportunities for thermal bridges, minimising the building form factor, and increasing the use of insulation.	Ongoing	X	X	X	X
31A The Council will implement policies from the overarching London Plan by requesting developers of large major schemes demonstrate the extent to which embodied carbon content informs their material choices, mandating all major schemes achieve operational net zero, and by encouraging new developments to minimise heat loss by reducing artificial surfaces, promoting green infrastructure, and using effective materials to enhance thermal performance.	Ongoing	X	X	X	X	X
32A The Council will use local planning policy to ensure that all new developments incorporate renewable energy generation, implement low-carbon heating systems, and achieve high energy efficiency standards wherever feasible.	Ongoing	X	X	X	X

# Theme 2: Sustainable, Connected Neighbourhoods

Introduction: How we travel around the borough has a significant impact on the borough’s emissions. Currently, transport emissions are the second largest sector of emissions here in Redbridge and they are generated by on road vehicles such as cars, lorries and vans which use petrol or diesel as a fuel source. These emissions not only contribute to climate change but also negatively affect local air quality and public health which can lead to residents facing a greater risk of developing respiratory conditions and other health related problems.
To start reducing harmful vehicle emissions in Redbridge, we have developed the theme ‘Sustainable, Connected Neighbourhoods’ which includes a comprehensive programme of projects, schemes and initiatives designed to bolster electric vehicle charging infrastructure within the borough, encourage residents to adopt active travel methods such as walking, cycling or using the local public transport network more readily, promote pedestrian priority in local town centres and support the transition away from petrol or diesel powered vehicles.
Long-Term Vision: Redbridge is a well-connected, sustainable borough where residents can get around using active travel methods such as walking, cycling, or using public transport. The public transport network is efficient, accessible, and powered by renewable energy, meeting the needs of all residents. Electric vehicle charging points are widely available, and the transition to electric vehicles has improved local air quality and positively impacted the physical health of residents.

Key achievements delivered so far:
- 469 electric vehicle charge points have been installed across the borough with more installations planned.
- Over 20km of cycle lanes have been delivered including segregated cycle lanes.
- 200+ cycle racks and bike hangars installed at locations all across the borough.
- 25 Council-owned vehicles were fitted with solar panels to help power their batteries and save fuel which was the largest trial in London.
- A new Electric Vehicle Strategy was designed to ensure accessible, reliable, and inclusive EV charging infrastructure for all residents, visitors, and businesses in Redbridge in the coming decade.
- The Council continued to strive for innovation and trialled a greener asphalt mix in highways maintenance projects which can reduce a road resurfacing projects carbon emissions by up to 68%.

Key Priorities:
1. Encouraging Active Travel Locally
2. Accelerating The Transition To Zero Emission Vehicles
3. Electrifying The Council’s Vehicle Fleet
4. Unlocking The Public Realm

Encouraging Active Travel Locally
Encouraging residents to use active travel methods such as walking to work, cycling to the shops, getting the bus or even scooting to school can significantly reduce the emissions we generate from travelling around the borough. Decreasing our reliance on petrol or diesel-powered vehicles also helps to improve local air quality and supports the physical health and mental wellbeing of the community as residents are able to lead more active, healthy lifestyles. Less cars on the road helps to alleviate traffic congestion and could offer local public health services economic savings as a healthier local population means less demand on key healthcare services. By delivering a series of projects such as connecting Ilford and the Roding Valley, improving traffic flow and safety in and around Ilford town centre, and enhancing pedestrian and cyclist safety at key junctions across the borough we can ensure that residents feel confident to travel around the borough safely without using personal vehicles which both supports residents to lead more active, healthier lifestyles and creates a more sustainable community.

Accelerating The Transition To Electric Vehicles
Electric vehicles produce significantly less emissions and have lower operating costs when compared to petrol or diesel powered alternatives but they also ensure that residents retain their personal independence. By increasing the amount of electric vehicle charge points located across the borough we will ensure that every resident can efficiently charge their vehicles at home, in the office and in the community which will encourage more people to make the switch and help reduce our transport emissions here in Redbridge. We will also consult local stakeholders to identify the most advantageous locations for charging infrastructure installations to ensure that we have a charging network that is tailored to the needs of the local community, and we will also support Transport for London in rolling out rapid charge points at TFL owned sites to ensure that residents and commuters have access to faster, more convenient charging options. By encouraging the use of electric car clubs amounts local employers, we also aim to make it easier for residents to access electric vehicles without owning one and reduce the number of vehicles on the road resulting in less traffic and lower emissions. All of these initiatives will make significant contributions in mitigating our impact on the climate and improving local air quality which will mean residents will be less likely to develop respiratory conditions and local health services may see reductions in demands for specific services. The widespread adoption of this new technology will also help to support economic growth as more employment opportunities will open up for skilled workers to support the delivery of key infrastructure programmes.

Electrifying The Council’s Vehicle Fleet
The Council has a sizeable vehicle fleet that it used to deliver key services such as collecting our bins, transporting key personnel and enabling officers to carry out necessary maintenance works. By electrifying our fleet and acquiring the most fuel-efficient vehicles, we can substantially reduce the amount of emissions our vehicles generate and enhance our fleet’s sustainability. Installing telematic systems on our vehicles will also enable us to improve the operational efficiency of our fleet by enabling more effective fuel consumption monitoring, evaluating driving practices and identifying the most optimal driving routes. Adopting innovative technologies such as installing solar panels on our vehicles to help power them will also reduce the fleet’s reliance on fossil fuels and enable the Council to support the borough’s broader climate goals by reducing transport emissions and promoting a cleaner, greener living environment. The combination of all these measures will also enable the Council to reduce the running costs of the vehicle fleet which will save the Council money in the long-term and enable more funding to be allocated to services supporting residents who are most in need.

Unlocking The Public Realm
Ensuring that our high streets, roads, parks and green spaces prioritise pedestrian safety and accessibility is essential. Everyone in the community including those in wheelchairs, mobility scooters, and pushchairs deserve the right to be able to travel around freely and reach every corner of the borough safely. By installing crossing points, widening pavements, and implementing traffic calming measures we aim to protect the safety of vulnerable road users and encourage residents to travel around the borough using active travel methods. Delivering initiatives such as developing walking maps for the public, carrying out an audit of the entrances to green spaces and installing additional cycle and scooter parking facilities help to improve accessibility to our green spaces and support residents to lead healthier, more active lifestyles.

Commitments		Outcomes
Detail	Timeframe	Carbon Reduction	Climate Resilience	Improved Public Health	Economic Benefits	Protect Biodiversity
Encouraging Active Travel Locally
33A The Council will establish physical connections between Ilford and the Roding Valley by March 2027 to promote active travel, reduce traffic congestion, and enhance accessibility.	Short-term (0-2 years)	X	X	X	X	X
34A The Council will develop the detailed design for the Ilford Western Gyratory project to improve traffic flow and safety in Ilford town centre by redesigning the current one-way system.	Short-term (0-2 years)	X	X	X	X	X
35A The Council will implement safety improvements for pedestrians and cyclists at key junctions, routes, and collision hotspots.	Ongoing	X		X	X
36A The Council will develop new active travel routes to green spaces in the borough to promote active travel, enhance accessibility and reduce reliance on motor vehicles.	Ongoing	X		X	X
37A The Council will review key gaps in the cycle network and identify opportunities to connect these areas by extending/enhancing existing cycle routes and creating new ones where feasible. As part of the assessment process, the Council will collaborate with local cycling community groups to assess proposed routes and identify any safety concerns that need addressing.	Medium-term (2-5 years)	X		X	X
38A The Council will enhance on-street cycle parking facilities across the Borough to accommodate commuter, residential, and leisure use. This initiative will involve the installation of cycle parking hangars and stands to provide secure and convenient parking options for cyclists.	Ongoing	X		X	X
39A The Council will lobby Transport for London (TfL) to enhance transportation infrastructure and services. This includes installing secure cycle parking facilities near TfL-owned stations, introducing lifts at key underground stations, gathering data on bus usage and congestion to optimise bus priority schemes and advocating for safer and more comfortable bus waiting environments with improved lighting and real-time information.	Ongoing	X		X	X
40A The Council will develop and deliver campaigns with Public Health to highlight the benefits of active travel, including its positive impacts on mental and physical health. These campaigns will engage schools, colleges, major employers, GP surgeries, and hospitals to promote walking and cycling as healthy, sustainable transportation options.	Ongoing	X		X	X
41A The Council will ensure that new developments are well served by reliable sustainable transport options and adhere to cycle parking and electric vehicle charge point standards.	Ongoing	X		X	X
42A The Council will support businesses and other employers across the Borough to better coordinate ‘last mile’ delivery services by encouraging information sharing to enable collaboration, coordination and timing of deliveries.	Long-term / (5-10 years)	X		X	X
Accelerating The Transition To Zero Emission Vehicles
43A The Council will develop a prioritised roll-out plan for the procurement of charge points across Redbridge’s car parks by utilising data from existing charge points to assess demand and strategically place additional charge points where needed.	Short-term (0-2 years)	X		X	X
44 The Council will support Transport for London's (TfL) objective to roll out rapid charge points at TfL-owned sites and collaborate on the joint delivery of hub development throughout the borough.	Medium-term (2-5 years)	X		X	X
45A The Council will continue with the progress of installing additional EV chargepoints for residential use, including planned procurement of up to an additional 1,000 EV chargepoints based on the objectives in the Council's Electric Vehicle Strategy. By delivering this key programme the Council aims to ensure that every resident is within at least a 5minute walk of a chargepoint by 2026 and 3 minute walk by 2030.	Short-term (0-2 years)	X		X	X
46A The Council will work in partnership with the Licensed Taxi Drivers Association and Private Hire Vehicle (PHV) operators, as well as other key stakeholders, to review evidence from existing electric taxi and PHV services. This collaboration aims to identify the most advantageous locations for installing charge points to facilitate the usage of electric vehicles among professional drivers.	Long-term / (5-10 years)	X		X	X
47A The Council will develop and oversee contracts to ensure the charging network is reliable, well-managed, and maintained, with obsolete infrastructure removed or upgraded as needed.	Ongoing	X		X	X
48A The Council will assist in the development and promotion of electric car club schemes, focusing on encouraging their use amongst local employers. The Council will also work towards increasing the number of electric car club bays in the borough to promote the use of shared transport options and support car sharing schemes.	Long-term / (5-10 years)	X		X	X
Electrifying the Council’s Vehicle Fleet
49C By the end of the financial year 2035/36, the Council will transition its entire vehicle fleet to battery electric vehicles (BEVs).	Long-term / (5-10 years)	X		X	X
50C The Council will install solar panel systems on an additional 17 Refuse Collection Vehicles by June 2026 to enhance the sustainability of the fleet by harnessing renewable energy to power auxiliary systems, thereby reducing reliance on traditional fuel sources. This initiative builds on the Council’s existing scheme, which already includes 25 vehicles such as refuse trucks, minibuses, and vans.	Short-term (0-2 years)	X		X	X
51C The Council will reinstall telematic systems across its entire vehicle fleet to enhance the monitoring of fuel consumption and this initiative aims to proactively implement measures that target a 10% reduction in fuel usage.	Short-term (0-2 years)	X		X	X
52C The Council will achieve the Mission Zero Fleet Accreditation to enhance our fleet’s safety, sustainability, and compliance.	Short-term (0-2 years)	X		X	X
53C The Council will continue to operate and maintain the existing fleet of battery electric vehicles which includes 13 vans, which are essential for the daily activities of various services within the organisation.	Ongoing	X		X	X
54C The Councill will purchase 20 of the most fuel-efficient dust carts by April 2026 where it is not possible for the vehicle type to be transitioned into electric.	Short-term (0-2 years)	X		X	X
Unlocking The Public Realm
55A The Council will introduce mobility hub schemes across the borough and following the success of pilot schemes in Wanstead and South Woodford, these schemes will be made permanent.	Long-term / (5-10 years)	X		X	X
56A The Council will develop walking maps for routes, including historic walking routes, leisure routes, and safe walking routes to schools, and improve active travel wayfinding in local centres and key destinations such as educational sites, hospitals, business parks, and travel hubs.	Long-term / (5-10 years)	X		X	X
57A The Council will increase pedestrian priority in local centres by increasing the number of crossing points, widening pavements, and introducing pedestrian crossing islands at junctions where feasible. The Council will consult with local communities to identify the most effective measures for each area and prioritise locations with high pedestrian demand and accident rates.	Ongoing	X		X	X
58 The Council will conduct a thorough audit of the entrances to green spaces and implement necessary improvements to enhance accessibility for people using wheelchairs, mobility scooters, pushchairs, and bicycles. Additionally, the Council will install additional cycle and scooter parking facilities near the entrances to parks and green spaces to encourage sustainable transportation and reduce carbon emissions.	Medium-term (2-5 years)	X		X	X
59A The Council will implement traffic calming measures in local centres, residential areas, and near educational sites to help reduce speeds. This initiative will include the installation of road humps, chicanes, and width restrictions to enhance road safety and protect vulnerable road users.	Ongoing	X		X	X

# Theme 3: A Climate-Resilient Green Borough

Introduction: As climate change intensifies and severe weather events become more frequent, we need to ensure that all residents are able to adapt and live comfortably. This means ensuring that our built environment and public spaces are designed in a way that protects residents against extreme temperatures, flooding, droughts and heatwaves. To address this, we have created the theme ‘A Climate-Resilient Green Borough’ to ensure that there is a broad range of projects, programmes and initiatives that support more sustainable living environments for residents by enabling the Council to manage flooding events more effectively, mitigate any risks posed by extreme weather conditions and integrate more green spaces to promote biodiversity and bolster climate resilience within the community.

Long-Term Vision: Everyone in the borough is equipped to manage climate impacts, with measures in place to protect residents from extreme weather events such as flooding, heatwaves and droughts. New buildings in the borough are built to a high specification and existing buildings have been upgraded so that residents have comfortable living conditions and are protected from extreme weather. Our public spaces are flourishing and green which both boosts climate resilience within the community and promotes biodiversity to safeguard local species and habitats.

Key achievements delivered so far:
- Over 65,000 new trees have been planted over the past decade.
- Over £1m of funding invested since the 2021 floods in Sustainable Drainage Schemes (SuDS).
- A new Local Flood Risk Management Strategy and Surface Water Management Plans were adopted in 2024.
- Over 100 state of the art gully sensors were installed at flooding hot spots to create a smart drainage system.
- Redbridge collaborated with regional bodies and partner organisations to secure over £500,000 in additional funding for innovative SuDS projects.
- The Council pledged £830,000 to support a package of flood defence measures planned for the next few years.
- Over 500 fruit trees were distributed in the community to provide canopy cover and support biodiversity in the borough.
- 20+ community gardens were adopted and cultivated by local gardening groups.
- 70+ on-street planters were adopted by businesses and community partnerships.

Key Priorities:
1. Safeguarding Residents From Flooding
2. Shielding Residents From Extreme Weather (Heatwaves and Cold Weather)
3. Greening Urban Spaces And Enhancing Biodiversity
Safeguarding Residents From Flooding
Flooding poses significant risks to residents as flash floods can cause the loss of property, damage local infrastructure, heavily disrupt public services and even threaten a loss of life. This risk is amplified in urban areas due to the widespread use of impermeable surfaces like concrete and asphalt which prevent water from draining into the ground and lead to higher volumes of surface water in our streets. By implementing effective flood risk management strategies and delivering targeted interventions we can help mitigate these risks to build climate resilience within our community and ensure that infrastructure and property is protected from costly damage. Measures such as using early warning systems to warn residents and local services of any flood risks, collaborating with regional risk management authorities, promoting the use of Sustainable Drainage Systems (SuDS) in building design and infrastructure projects, and delivering general awareness campaigns all help to bolster community preparedness and ensure that protective measures are in place to help protect our residents.

Shielding Residents From Extreme Weather (Heatwaves and Cold Weather)
Extreme weather conditions such as freezing temperatures and heatwaves, all pose serious health risks to the community with the older and younger generations being especially vulnerable due to their limited ability to adapt. To address these challenges and ensure that we implement sufficient protective measures, a multifaceted approach is needed. By developing effective emergency response strategies, delivering community preparedness initiatives and adapting or designing buildings so they combat cold weather in the winter and stay cool during the summer we can build climate resilience within the community and ensure that our residents stay safe and healthy. Encouraging the use of green roofs and walls in building design, promoting the locations of cooling centres during heatwaves, and collaborating with public health officials to develop an effective Heatwave Response plan will also help to ensure that Redbridge is well adapted to meet the challenges posed by extreme weather conditions in the future.

Greening Urban Spaces And Enhancing Biodiversity
Installing greenery into our residential roads, high streets and public spaces helps to support local biodiversity and create a more sustainable and liveable borough. Green spaces, such as parks and community gardens, offer a variety of ecological and social benefits, as plants acts as natural air filters and help to reduce the urban heat island effect whilst parks provide residents with recreational opportunities. To ensure nature in Redbridge remains in balance we need to protect native species and create new wild spaces to ensure animals have access to a broad range of habitats. Greening urban spaces also helps to boost climate resilience within the community and support public health as green infrastructure such as trees provide residents with shade during hotter periods and help to drain away rainwater through the soil during flooding events. By conducting ecological assessments, establishing nature buffer zones, applying biodiversity net gain requirements on developers, supporting community led green projects and collaborating with the Greater London Authority on the Local Nature Recovery Strategy we will ensure that our borough remains a vibrant, sustainable place for residents and wildlife to thrive for years to come.

Commitments		Outcomes
Detail	Timeframe	Carbon Reduction	Climate Resilience	Improved Public Health	Economic Benefits	Protect Biodiversity
Safeguarding Residents From Flooding
60R The Council will send infectious disease prevention and control messages to residents during flooding events and collaborate with key health partners from the UKHSA, NHS, and Social Care to manage infectious outbreaks. Public Health will also continue local horizon scanning for infectious diseases and contribute to UKHSA-led national and international efforts.	Ongoing		X	X	X
61R The Council will review and update the Flood Risk Management web pages on its website and include detailed information on the purpose and benefits of Sustainable Drainage Systems (SuDS). The Council will also provide case studies on successful flood alleviation schemes and include the latest data, resources, and guidance to help residents understand and mitigate flood risks.	Ongoing		X	X	X
62R The Council will establish and maintain a Flood Risk Asset register detailing the ownership and state of repair of all flood risk assets, with regular updates to ensure optimal maintenance and proactive flood risk management. Additionally, the Council will produce and maintain a list or map of high-priority areas for flood alleviation schemes, based on flood risk severity and social, economic, and environmental indicators, regularly updating this resource to reflect the latest data and insights.	Ongoing		X	X	X
63R The Council will deliver targeted flood alleviation schemes based on detailed investigations of significant flooding incidents.	Ongoing		X	X	X
64R The council will collaborate with risk management authorities, land managers, and the community to identify opportunities for incorporating natural flood management within Redbridge. The Council will also establish and maintain regional connections with flood risk partnerships to enhance communication between risk management authorities in the North-East London area.	Ongoing		X	X	X	X
65R The Council will support an increase in resident uptake of property-level flood resilience and mitigation measures. The Council will also collaborate with relevant internal teams, the finance sector, Flood Re, and local communities to provide guidance and resources.	Ongoing		X	X	X
66R The Council will require developers to demonstrate that no flooding will occur in any part of a proposed building up to and including a 1 in 100-year rainfall event and developers must also ensure that flows from rainfall exceeding a 1 in 100-year event and mitigate flooding risks to people and property in flood zones.	Medium-term (2-5 years)		X	X	X
67R The Council will introduce Sustainable Drainage System retrofitting policies and incentives.	Ongoing		X	X	X	X
68R The Council will incorporate Sustainable Drainage Systems (SuDS) into future public realm and highways schemes where feasible and introduce SuDS and other Flood Alleviation schemes targeting key flood hotspot locations and known areas of surface water and sewer flood risk.	Ongoing		X	X	X	X
69R The Council will work with partner organisations to support community-targeted water butt or other flood protection schemes.	Ongoing		X	X	X
70R The Council will request that developers fully assess the potential for flooding in new developments and implement mitigation measures to reduce surface water run-off where required which includes measures such as the incorporation of Sustainable Urban Drainage Systems (SUDS) and landscaping methods to manage water flow effectively.	Ongoing		X	X	X	X
71R Using the Council's Policy for Footway Crossings as the guiding document, the Council will explore the possibility of delivering schemes that incentivise residents to transform their front gardens from concrete to more permeable, natural surfaces contingent on external funding being secured.	Medium-term (2-5 years)		X	X	X	X
72R The Council will lobby National Government to implement Schedule 3 of the Flood and Water Management Act 2010, or other enhanced tools, to reduce flood risk and improve water quality management in new developments and redevelopments.	Short-term (0-2 years)		X	X	X	X
Shielding Residents From Extreme Weather (Heatwaves And Cold Weather)
73R The Council will promote the integration of green roofs and walls in building designs to help mitigate the effects of the urban heat island effect.	Ongoing	X	X	X	X	X
74R The Council will continue to support the operation and promotion of cool centres in public libraries, community centres, schools, and parks to provide residents with relief during heatwaves, prioritising these locations in vulnerable communities where possible.	Ongoing		X	X	X
75R The Council will maintain collaboration with public health officials and borough partners to implement a comprehensive borough-wide Heatwave Response plan.	Ongoing		X	X	X
76R The Council will launch public awareness campaigns on heatwave preparedness and self-care, utilising all available mediums such as Redbridge Life, ensuring that vulnerable and underserved communities receive targeted messaging to stay safe and informed during extreme heat events.	Ongoing		X	X	X
77R The Council will promote heatwave awareness, cold weather preparedness, and general health education at the Care Provider Forum to ensure that care providers are well-prepared to protect vulnerable residents from heat-related and cold weather risks.	Ongoing		X	X	X
78R The Council will consistently monitor extreme weather alerts from the UKHSA and UK Met Office and disseminate this information to social care providers in the borough, ensuring that vulnerable residents are prepared and protected from extreme weather incidents. Additionally, Public Health will continue to work closely with the Civil Protection Team to maintain an effective borough-wide alert system for extreme weather warnings.	Ongoing		X	X	X
79R The Council will continue developing a Vulnerable Individuals Plan to identify vulnerable individuals during a formally declared major incident by Category 1 responders.	Short-term (0-2 years)		X	X	X
80R The Council will request developers clarify how their proposals have been informed by an analysis of solar gain and cooling loads by assessing factors such as the proportion of glazing to building fabric and the shading strategy are carefully considered in the building envelope design.	Ongoing	X	X	X	X
Greening Urban Spaces And Enhancing Biodiversity
81B The Council will conduct a comprehensive borough-wide spatial data review of all Sites of Importance for Nature Conservation (SINC) and adjoining areas.	Short-term (0-2 years)			X		X
82B The Council will explore suitable buffer zones to initiate ecological and environmental assessments for proposed developments near areas which have been designated as Sites of Importance for Nature Conservation (SINC) and/or Sites of Special Scientific Interest (SSSIs).	Short-term (0-2 years)			X		X
83B The Council will work with the Greater London Authority (GLA) to develop the London Local Nature Recovery Strategy to ensure that the Strategy reflects the needs of Redbridge's population.	Short-term (0-2 years)	X	X	X	X	X
84B The Council will ensure biodiversity net gain (BNG) requirements are applied on all applicable developments to enhance biodiversity in Redbridge.	Ongoing		X	X	X	X
85B The Council will partner with community groups to enhance existing community gardens or where permitted establish new community gardens, orchards and pocket parks which support biodiversity prioritising partnering with community groups in areas with less available green space and higher levels of deprivation.	Medium-term (2-5 years)	X	X	X		X
86B The Council will continue to deliver the Council’s commitment to create up to 160,000sqm of wild spaces, focusing on areas that lack green spaces and serve low-income communities.	Medium-term (2-5 years)	X	X	X		X
87B The Council will support community led projects and initiatives such as the Adopt a Tree Pit scheme, Pollinator Pathways and the 2025 resident Restore Nature Pledge for private households and community groups to further support biodiversity in Redbridge with a focus on areas with higher levels of deprivation and less available green space.	Ongoing	X	X	X	X	X
88B The Council will identify and apply for external funding to deliver a potential programme of tree planting to address areas where low tree canopy cover has been highlighted as an issue.	Short-term (0-2 years)	X	X	X	X	X
89B The Council will deliver on the Greater London Authority's (GLA) funding commitments to increase publicly available wild spaces as part of the Ilford Arrival Scheme.	Short-term (0-2 years)	X	X	X	X	X
90B The Council will deliver a tree planting and replacement programme across the Council's housing stock. This will include specific targets where possible and will be contingent on external grant funding.	Ongoing	X	X	X		X

# Theme 4: A Thriving Green Economy

Introduction: As the global economy transitions towards greener practices, we need to ensure that the local economy in Redbridge also evolves so that businesses and workers can take full advantage of any opportunities as they emerge. By promoting sustainability in the local business sector, we can also ensure that businesses remain competitive and can thrive as they will have lower operating costs. To achieve this, we have developed the theme ‘A Thriving Green Economy’ which includes a series of actions that will ensure that residents have a wide range of opportunities to learn new green skills to improve their employability, sustainable businesses will view Redbridge as a target location to establish themselves, residents will be able to adopt more sustainable ways of living, and the Council will be able to improve the sustainability of the organisation’s supply chain and challenge companies to support the borough’s broader net zero ambitions.

Long-Term Vision: The local economy in Redbridge is a vibrant business community where sustainability is at the heart of everyday life. Residents are equipped with green skills that open doors to new job opportunities in emerging industries and local businesses prioritise more sustainable practices. Residents have access to a wide range of services that enable them to reuse, recycle, and refurbish goods which reduces household waste and helps to conserve resources. The Council's supply chain is robust and environmentally responsible with local suppliers trialling innovative practices and striving for greener standards.

Key achievements delivered so far:
- The Pension Fund switched 50% of investments to low carbon equity units which reduced the fund’s carbon footprint by up to 31%.
- The climate change agenda and sustainable purchasing has been embedded into the Council’s updated Procurement Strategy.
- “Meet the Buyer” events held to guide supplies on climate initatives and to drive innovation within the organisation’s suply chains.
- Business forums delivered on a quarterly basis to rasei awareness on sustaianbility within the local business sector.
- The Council partnered with the Redbridge Institute of Adult Education to establish a Green Skills Hub which offers courses that enable residents to access employment opportunities within the green economy.
- The Council hosted the first ‘Green Skills Summit’ in 2024 which brought together local employers, supply chain partners and skills providers to work together to promote green skills and susutaianbility initiatives in the borough.
- 2 community-led repair cafes are now operating and funded in the borough, supporting residents with repairing household items and clothes.
- 100+ nappy packs distributed to parents in the borough to support parents to move away from using disposable nappies.

Key Priorities:
1. Expanding The Local Green Skills Offer
2. Supporting Sustainable Business To Flourish In Redbridge
3. Fostering A Circular Economy In Redbridge
4. Implementing Sustainable Procurement Practices

Expanding The Local Green Skills Offer
As the global economy transitions towards greener practices, we need to ensure that the local workforce is equipped with the skills needed to meet the demands of emerging industries. Learning green skills enhances employability and increases financial resilience within the community as workers are able to take full advantage of opportunities within the green economy. By hosting an annual Green Skills Jobs Fair, launching awareness campaigns focused on green industries, and developing robust career pathways in sectors like domestic retrofit and electric vehicle charging infrastructure we can ensure that local training programmes effectively meet local business needs and enable residents to secure sustainable employment and thrive in the evolving green economy.

Supporting Sustainable Business To Flourish In Redbridge
Sustainable businesses form the backbone of any environmentally responsible local economy by prioritising business practices that minimise environmental impact. These special types of enterprises also help to embed the values of sustainability in the local community and spark important conversations around the kitchen table on consumption levels and the carbon cost of the goods we are consuming. By mapping the sustainable business landscape, creating a green business directory and offering affordable workspaces to green businesses we can support the local sustainable business community to thrive here in Redbridge.

Fostering A Circular Economy In Redbridge
A circular economy revolves around residents reusing, recycling, repairing or refurbishing goods so that they remain in use for as long as possible. This approach helps to conserve natural resources and reduce the emissions that we generate from waste as new household items are purchased less frequently. These changes can also help stimulate local economic activity as they support businesses in areas such as sustainable manufacturing, furniture refurbishment or waste management and recycling roles. By promoting local community groups which offer repair or refurbishment services and collaborating with businesses to develop local circular economy initiatives, we can support residents to reduce consumption levels and adopt more sustainable lifestyles.

Implementing Sustainable Procurement Practices
The Council plays an important role as a local commissioner as not all services can be delivered by teams within the organisation and instead have to be outsourced to external companies. It is essential that the Council acts responsibly and enters into contracts with companies who can deliver the required services in a way which has minimal impact on the environment but also guarantees a high level of service for our residents. Sustainable procurement practices help to formalise this approach and drive forward sustainability within the local market as suppliers battle to adopt greener standards to improve their chances of winning contracts with the Council. By delivering key actions such as raising awareness on sustainability measures among local suppliers, introducing sustainable procurement initiatives at project kick-off meetings, and supporting contract managers to develop effective sustainability targets for external companies, we can ensure that the Council sets a strong standard in promoting environmental responsibility and helps to foster a more sustainable and efficient local economy.
Commitments		Outcomes
Detail	Timeframe	Carbon Reduction	Climate Resilience	Improved Public Health	Economic Benefits	Protect Biodiversity
Expanding The Local Green Skills Offer
91A The Council will deliver a Green Skills Jobs Fair to showcase recruitment and training opportunities within the green economy, connecting job seekers with local employers and training providers. Additionally, the Council will launch awareness campaigns to inform residents about green skills and career opportunities.	Short-term (0-2 years)	X			X
92A The Council will carry out a mapping exercise with senior decision makers at the Council, representatives from partner organisations, and local employers to understand what major projects, programmes, and developments are currently being delivered and are scheduled to be delivered in the future, to ensure an accurate long-term view of development in Redbridge over the next 10 years.	Short-term (0-2 years)	X			X
93A Following the mapping exercise, the Council will create a development pipeline for Redbridge, detailing existing and planned developments over the next 10 years. This pipeline will be a live document, updated every six months, and shared with local employers and partner organisations. This will ensure that social value and Section 106 offers are tailored to meet local business needs, fostering alignment with and maximising community benefits.	Short-term (0-2 years)	X			X
94A The Council will partner with Redbridge Institute and other local providers to enhance the training programmes at the Green Skills Hub, designing green skills courses, vocational training programmes and apprenticeship schemes that align with local business needs through ongoing collaboration with key contractors and suppliers.	Short-term (0-2 years)	X			X
95A The Council will consider implementing programmes like Design Engineer Construct (DEC) in schools to introduce students to green skills early. This initiative will draw on best practice models from neighbouring boroughs, ensuring that students gain valuable insights into sustainable construction and engineering.	Short-term (0-2 years)	X			X
96A The Council will collaborate with developers, contractors, and suppliers to include green skills training as part of Section 106 agreements.	Short-term (0-2 years)	X			X
97A The Council will partner with Redbridge Institute to deliver a Green Skills Summit on an annual basis subject to feasibility to create clear pathways for residents to access opportunities within the green economy.	Short-term (0-2 years)	X			X
Supporting Sustainable Business To Flourish In Redbridge
98A The Council will conduct a mapping exercise to gain a comprehensive understanding of the sustainable business landscape in the borough. This initiative will identify key businesses and sectors leading in sustainability, providing valuable insights for future support and collaboration.	Medium-term (2-5 years)	X			X	X
99A The Council will create a green business directory to increase visibility for climate-focused businesses within the community which will enable residents to identify and support local businesses committed to sustainability.	Medium-term (2-5 years)	X			X	X
100A The Council will ensure that the Queen Victoria House Business Hub offers affordable workspace to support local eco-friendly businesses.	Short-term (0-2 years)	X			X	X
101A The Council will actively promote the benefits of sustainable businesses through our communication channels to increase local support.	Ongoing	X			X	X
102A The Council will design a comprehensive programme to support sustainable businesses within Redbridge.	Medium-term (2-5 years)	X			X	X
103A The Council will continue to explore and apply for external grant funding to further develop programmes supporting sustainable businesses in Redbridge.	Ongoing	X			X	X
Fostering A Circular Economy In Redbridge
104A The Council will deliver communication materials to educate residents and businesses on the benefits of a circular economy.	Ongoing	X			X	X
105A The Council will collaborate with local businesses to develop and promote circular economy initiatives, such as repair services for electrical items and textiles.	Short-term (0-2 years)	X			X	X
106A The Council will promote local businesses offering repair, refurbishment, or rental services as an alternative to new purchases, for example, by promoting the ReLondon Repair Directory.	Short-term (0-2 years)	X			X	X
Implementing Sustainable Procurement Practices
107A The Council will promote awareness of sustainability measures among local suppliers by organising information campaigns and providing resources on best practices where applicable.	Short-term (0-2 years)	X		X	X	X
108A The Council will introduce sustainable procurement initiatives at each project kick-off meeting and encourage stakeholders to incorporate relevant sustainability criteria into tender documents.	Short-term (0-2 years)	X		X	X	X
109 The Council will support contract managers to develop Key Performance Indicators (KPIs) for evaluating supplier performance and increase targets as needed to drive continuous improvement and ensure that suppliers meet the highest sustainability standards.	Short-term (0-2 years)	X		X	X	X
110S The Council will encourage the consideration of the climate change agenda at the Council's Strategic Commissioning Board (SCB) to ensure that climate priorities are integrated into strategic discussions and decision-making processes.	Short-term (0-2 years)	X		X	X	X
111C The Council will identify relevant existing contracts and collaborate with contract managers to incorporate appropriate climate-specific Key Performance Indicators (KPIs).	Short-term (0-2 years)	X		X	X	X
112 The Council will identify and benchmark examples of good practice in neighbouring boroughs and aim to replicate or exceed these standards where possible in Redbridge.	Medium-term (2-5 years)	X		X	X	X

# Theme 5: Climate-Conscious Communities

Introduction: Everyone's participation is crucial to ensure that Redbridge’s transition to net zero is successful. The collective actions of everyone in the borough, big or small, can significantly reduce our borough’s emissions and ensure that we secure a sustainable future for generations to come. To achieve this, we have developed the theme ‘Climate Conscious Communities’ which features a programme of actions that aim to empower residents to live more sustainable lifestyles through learning new information and putting new skills into practice, encourage community participation for residents to take a leading role in supporting and delivering local climate initiatives and ensure that children and young people are at the forefront of climate action here in Redbridge.

Long-Term Vision: Residents are well-informed on the benefits of community climate action and understand their crucial role in supporting the broader environmental goals of the borough. Residents, local businesses, and community groups, receive ample support to make sustainable choices and have access to a wide range of networks and resources which fosters a more cohesive, sustainable society.

Key achievements delivered so far:
- 400+ households received valuable advice on reducing waste to save money and carbon emissions.
- Wheelie bins rolled out to 85,000 properties in 2021 as part of the Council’s Waste Management Strategy.
- Delivered various behaviour change campaigns and workshops which resulted in a 13% reduction in avoidable food waste per capita.
- Surpassed target on reducing household waste with the monthly average recording in at 51kg.
- 27 registered Play Street schemes are active in closing their streets to cars on a monthly basis.
- 500+ children took part in tree planting projects at schools.
- 6 schools supported to open pre-loved uniform banks.
- 25 schools given small grants to deliver their sustainable travel projects.
- 19 School Street schemes in operation covering 21 schools.
- 1,300 bikes checked by the Dr Bikes school sessions.
- 2000+ children received pedestrian skills training.
- 21 secondary schools took part in annual youth climate events in recent years.
- Climate themed assemblies and workshops delivered to over 3,000 pupils.
Key Priorities:
1. Empowering Residents To Become More Eco-Friendly Households
2. Engaging With The Local Community
3. Further Embedding Child Friendly Principles

Empowering Residents To Become More Eco-Friendly Households
Equipping residents with the necessary knowledge and skills to adopt more sustainable behaviours at home is a crucial part of the borough’s net zero journey. When residents are well informed, they are more likely to engage in practices such as recycling, home composting, and adopting more sustainable consumption behaviours which all directly reduce household emissions. Providing resources such as skills workshops in the community, accessible facilities, food waste collections and affordable home composting bins can help to empower residents to take proactive measures to positively contribute to reducing the borough’s emissions. The Council will also collaborate with the East London Waste Authority (ELWA) on a wider strategic piece to deliver the Waste Prevention Plan and ensure that residents have access to a high quality, sustainable waste collection service.

Engaging With The Local Community
Community engagement is an essential step in developing robust strategies that are both impactful and effective in meeting the needs of the community. By consulting with residents across the borough, we can harness diverse perspectives to tailor local environmental initiatives so that they are more inclusive and ultimately more successful. This close collaboration enables residents to take a more proactive role in shaping local climate policy and builds greater community ownership on driving forward the borough’s transition to net zero. By encouraging community participation in submitting funding applications for local sustainability projects, hosting the local public green network called the Redbridge Climate Forum and providing more opportunities for residents to provide feedback on sustainability initiatives we can ensure that residents voices are heard and at the forefront of local climate action here in Redbridge.

Further Embedding Child Friendly Principles
Adopting child-friendly principles ensures children and young people are recognised as not only future stakeholders but also current members of the community who can provide valuable perspectives and innovative ideas to shape local climate policy. Engaging younger residents in local climate action helps to strengthen long term ownership on environmental sustainability and enhances the inclusivity of policymaking here in Redbridge. The Council is committed to prioritising the involvement of younger generations in community climate action efforts for years to come and will deliver actions such as delivering more school streets schemes, involving young people in community gardening projects and delivering tree planting programmes in partnership with schools and community groups.

Commitments		Outcomes
Detail	Timeframe	Carbon Reduction	Climate Resilience	Improved Public Health	Economic Benefits	Protect Biodiversity
Empowering Residents To Become More Eco-Friendly Households
113A The Council will deliver local communication materials to educate residents on the importance of waste minimisation, what tips they can follow to reduce household energy consumption, and how they can get involved with regional and national awareness events.	Ongoing	X		X	X	X
114A The Council will work in partnership with local community groups to deliver eco skills workshops in the community which focus on how residents can repair electrical items, reduce food waste, create compost at home, and grow their own vegetables.	Ongoing	X		X	X	X
115A The Council will provide cheaper compost bins to residents where external funding or support is made available, and the Council will also support the widespread adoption of home composting methods through educating residents on how they can reduce their household waste.	Ongoing	X		X	X	X
116A The Council will support the establishment of additional community composting sites throughout Redbridge.	Short-term (0-2 years)	X		X	X	X
117A The Council will deliver sustainable waste management information to the community in a variety of ways such as practical sessions at ESOL classes, at landlords/tenants workshops, and via the ongoing side waste action project which identifies the highest waste producing households and supports them to reduce waste with specific guidance.	Ongoing	X		X	X	X
119A The Council will enhance recycling services in the borough in line with the UK government's Simpler Recycling reforms and will seek to optimise opportunities brought forward by the new ELWA Waste Disposal contract starting in 2027.	Medium-term (2-5 years)	X		X	X	X
120A The Council will work in close collaboration with the East London Waste Authority (ELWA) to deliver the Waste Prevention Plan.	Ongoing	X		X	X	X
121A The Council will implement mandatory separate food waste collections taking a phased approach, with the first phase commencing in Autumn 2025.	Short-term (0-2 years)	X		X	X	X
121 The Council will provide support to local food banks and community organisations which form part of the Redbridge Food Partnership that provide food to residents who are experiencing financial difficulties.	Ongoing	X		X	X	X
122 The Council will actively promote the Healthy Start scheme and where feasible fund local foodbanks to ensure families have access to nutritious, affordable food. Initiatives include supporting food affordability programs and collaborating with the community to develop sustainable food solutions.	Ongoing	X		X	X	X
Engaging With The Local Community
123C The Council will develop a compelling narrative for Redbridge through the drafting of annual reports which highlight the progress that has been achieved on the carbon reduction and sustainability programmes the organisation has delivered and the impacts that have been measured. The Councill will also continue to advocate for increased resources and backing from central government by lobbying as a collective as part of London Councils.	Short-term (0-2 years)	X	X	X	X	X
124 The Council will deliver two meetings of the Redbridge Climate Forum per year to gather input, feedback, and support from residents on the Council’s work on carbon reduction and sustainability. The Council will seek to increase the forum's membership and improve engagement and participation from residents in economically disadvantaged areas, ensuring diverse community involvement and more effective climate action.	Ongoing	X	X	X	X	X
125C The Council will organise workshops and public consultations on key climate projects and policies, ensuring that initiatives are effective in meeting the needs of the community	Ongoing	X	X	X	X	X
126A The Council will encourage residents and community groups to participate in funding applications for climate initiatives.	Ongoing	X	X	X	X	X
Further Embedding Child Friendly Principles
127 The Council will work in partnership with local schools to deliver a climate focused engagement event or activity with children and young people each year.	Ongoing	X	X	X	X	X
128 The Council will encourage young people to attend and participate in the Redbridge Climate Forum.	Ongoing	X	X	X	X	X
129A The Council will deliver planting programmes with community groups and children and young people in Redbridge, contingent on available funding.	Ongoing	X	X	X	X	X
130A The Council will implement School Streets schemes at all locations with educational sites where feasible.	Short-term (0-2 years)	X		X	X	X
131A The Council will continue to deliver cycle training and pedestrian skills programs and expand to more schools where possible, contingent on external funding continuing.	Ongoing	X		X	X	X
132A The Council will encourage and promote the establishment of walking buses by collaborating with schools and community groups to create safe and convenient walking routes for children.	Ongoing	X		X	X	X
133 The Council will develop a Sustainability Plan for the Child Friendly Redbridge Programme to ensure that the voices of children and young people are central in decision-making processes for major climate-focused strategies, action plans, and programmes.	Short-term (0-2 years)	X	X	X	X	X
134 The Council will promote and support the Eco Schools initiative, encouraging more schools to participate and achieve recognition for their environmental efforts.	Ongoing	X		X	X	X
135 The Council will consider and produce an offer for schools related to sustainability each year based on opportunities.	Ongoing	X	X	X	X	X

# How can you keep up to date with our progress?
In this Climate Change Strategy, the Council has committed to delivering a staggering 135 actions which cover 19 number of priorities that are all of vital importance. To keep us on track with delivering these ambitious actions, we will carry out quarterly internal reporting for each of the 135 commitments so that we can see what progress is being achieved under each area and what barriers are in place which may need consideration.

To ensure transparency, at the end of each reporting year the Council will publish a full report on the organisation’s website which will be available to everyone, and this report will provide full details of the progress that services have reported. We will also provide residents with ample opportunities to provide feedback on climate action here in Redbridge through regular public consultations, workshops and meetings of public networks such as the Redbridge Climate Forum. We will also promote any success stories or notable achievements through our established communication channels and continue to carry out close engagement with the community on any new climate initiatives to ensure that we are delivering projects that are tailored to the community’s needs. By taking these actions, we plan to ensure that the Council remains open and accountable in delivering the Climate Change Strategy.
# How will the Climate Change Strategy be funded?
Delivering all of the commitments in the Climate Change Strategy will require a significant amount of funding and resources in order to be successful. As tackling the climate emergency is a key priority for the Council, the vast majority of commitments in the Strategy have been agreed in line with existing budgets and resources.

However, we are keen to increase our level of ambition and services will continue to actively identify and apply for additional funding for key climate focused projects and programmes from a wide variety of sources within both the public and private sector including government grants and private sector investments. The Council will also assess any new innovative funding models such as community bonds to ensure that all financial options are explored, and we will also continue to lobby central government to leverage additional funding for key climate programmes here in Redbridge.
# What changes will you make today?
To become a net zero borough, everyone living and working in Redbridge will need to come together and work as a collective to drive forward local climate initiatives and drastically reduce our borough’s carbon footprint. This also means taking an honest look at individual lifestyles and behaviours and seeing if there are any simple changes that you can make such as walking to the local shop instead of driving, being mindful of recycling when disposing of items at home and seeing if there are any sustainable practices that you could potentially incorporate into your daily lifestyle.

This transition may feel as though it is a huge task but any changes that you are able to make will be meaningful and count as another step in the borough’s long term transformational journey. We do need a major societal change to happen and that will take the combined effort of every resident, local business (big or small), community group, school, place of worship, partner organisation and service at the Council to play their part as this is the only way that we can secure a sustainable future for generations to come.

In this Climate Change Strategy, we have outlined a broad range of actions that we will take today to start affecting positive change here in Redbridge but as you can see from our emissions data, the largest sectors of emissions start at home so please consider what actions you will take or what local initiatives you will support and make the change today.

# Appendix: List Of Related Strategic Documents

Local Policy Documents:
- Redbridge Local Plan (2015-2030)
- Redbridge Parking Strategy (2020-2025)
- Redbridge Air Quality Action Plan (2020-2025)
- Redbridge Green Urban Landscape Policy for Council Maintained Land (2021-2024)
- Redbridge Employment, Skills and Enterprise Strategy (2022-2027)
- Redbridge Plan (2022-2026)
- Redbridge Reduction and Recycling Plan (2023 – 2025)
- Redbridge Housing Strategy (2023-2028)
- Redbridge Electric Vehicle Strategy (2024-2033)
- Redbridge Sustainable Transport Strategy (2024-2041) (DRAFT)
- Redbridge Local Flood Risk Management Strategy (2024-2030)
Regional Policy Documents:
- The London Plan – The spatial development strategy for Greater London (2021)
- ELWA Waste Prevention Programme Action Plan (2024-2025)
National Policy Documents:
LETI Climate Emergency Design Guide – How new buildings can meet UK climate change targets (2020)